## Overview
DevRel Bird's Eye / WIP (Work In Progress)
Captured from OneNote content ¦ Source date in note: Tuesday, January 30, 2024 10:28 AM
Section | Details
DevRel high level check-in objectives | Reduce standing meetings that needlessly consume calendar blocks; communicate project resource conflicts and overlapping deadlines; clarify relative priorities across simultaneous projects; keep this meeting at overview level (Project vs Project) for full-team audience; improve org-level overview for the entire team.
Project intake | 1) Send video requests to USF form: https://aka.ms/DevRelStudiosSubmission 2) Proposals reviewed in Content Review meeting 3) After approval, EP meets with content owner 4) EP updates parent ADO item with episode items for creative team execution
CoreIdentity Entitlements for ADO access | Studios ADO Entitlement: https://coreidentity.microsoft.com/manage/Entitlement/entitlement/studiosadopr-gyl1
DevRel Studios documentation wiki | DevRel Studios wiki: https://dev.azure.com/devrel/Studios/_wiki/wikis/Studios.wiki/6301/DevRel-Studios
Run of Show template | DevRelStudios_ROS_Template: https://microsoft.sharepoint.com/:x:/t/MicrosoftDeveloperStudiosChannel9/EZdkE5pjzK9DgSzGXyk1Jo4Bi7PL3RMFkWJgIEOvETCmsQ?e=rrXkI4
Social platforms guidelines | MSDev Social Creative Overview for Videos.pptx: https://microsoft-my.sharepoint.com/:p:/r/personal/chrbooth_microsoft_com/Documents/MSDev%20Social%20Creative%20Overview%20for%20Videos.pptx?d=wc76987b3912546c8b8451c6e75414406&csf=1&web=1&e=X9WMIU
Studio JunkDrawer | Studios Ops JunkDrawer Backlog: https://dev.azure.com/devrel/Studios/_backlogs/backlog/Studios%20Ops/JunkDrawer
Person with agenda item | ADO (optional) | Relevant dates | Info/Discussion | Action items / Questions
Cameron / Matt |  | Find a week to go dark - likely mid Aug | Summer studio organization | Team to identify summer OOF windows and land on a week for cleanup/organization.

## Production
Production - Active Projects
Timeframe | Active project | EP | Type | Recording dates | TD | Location | Notes
THIS WEEK | Data Exposed (ADO 182486) | Ross | Show | 5/18 | Anna H | StreamYard
THIS WEEK | GitHub Copilot Dev Days (ADO 230864) | Cameron | Event | 5/27 | Matt | Studio - Stages A & C
THIS WEEK | Cozy AI Kitchen (ADO 182227) | Ross | Show | 5/29 | Matt | Studio - Stage A | Guests: General Robotics reshoot, Rohan Malpani, Thoa Nguyen, Stacey Mulcahy
NEXT WEEK | Data Exposed (ADO 228525) | Ross | Show | 6/1 | Anna H | StreamYard
NEXT WEEK | GLEAM Pride 2026 Virtual Kick off - pre-record (ADO 221377) | Kaitlin | Pre-record | 6/2 | Matt | StreamYard
NEXT WEEK | Microsoft Build 2026 (ADO 225153) | Golnaz / Kaitlin | Event | 6/2 - 6/3 | On location | On location - SF | Live stage; content planning file noted in source. EP assignments: Kaitlin + Anna (red/blue Day 1), Sara + Kavita (yellow/green Day 2), Aurea (photography/thumbnails), Cameron (breakout), Ross (interstitial content).

## Pre-Production
Pre-Production - Active Projects
Active project | EP | Type | Relevant dates | Location | Status | Action items / Questions
Fabric Tech Talk Fridays (ADO 174864) | Golnaz | Show | June, TBD | StreamYard | Scheduling | 2 new episodes to schedule for early June.
GLEAM Pride 2026 Virtual Kick off (ADO 221377) | Kaitlin | Event | 6/10 | Studio | Scheduling | Content owner: Carlos Herquinio. ASL interpreters requested through RUN and confirmed, waiting on info. Green room reserved. Need session invite to Rain and other in-person presenters and crew invite. Note: Kaitlin to send invites while Allison is OOF/medical.
Quest to Compile (ADO 214995) | Sara | Series | 6/11 | Studio - Stage C | Scheduled | StreamYard self-service, in studio (recording 3 episodes).
Avatar shoot - Rick Claus (ADO 228439) | Aurea | Series | 6/11 | Studio - Stage A (green screen) | Scheduled
.NET Day of Agentic Modernization 2026 (ADO 222161) | Cameron | Event | 6/16 | StreamYard | Scheduling | Half-day (9am-1pm) StreamYard event, Matt as TD. Presenters/hosts all remote (7 sessions). All pre-records scheduled for 6/8. Sessions need to be added to ADO.

## Planning
Development & In Planning
Fiscal period | Project | EP | Type | Relevant dates | Location | Greenlit or Uncertain | Notes / Action items
FY26 - Q4 | Build Your Personal Portfolio Website in Minutes: AI-Powered Coding for Students (ADO 227810) | Cameron | Series | 6/22 - 6/26 | TBD | In planning | Episode info needed in ADO. Chris working on branding. Holding week of 6/22 for recording (mix of studio and location). Could be pushed into FY27 - update needed.
FY27 - Q1 | Pure Virtual C++ (ADO 230213) |  |  |  | Likely virtual |  | Producing 8-10 on-demand sessions? Hosts TBD (Sinem Akinci? Erika Sweet?). Kaitlin waiting on content owner (Marion).
FY27 - Q1 | Visual Studio Live! @ MSHQ session recording (ADO 231304) |  | Proposal - Event | 7/27 - 7/29 | Commons (B98) + B92 + Studio for VST episodes |  | Want capture of 3 days instead of 2, plus some VST episodes in studio (with Leslie Richardson).
FY27 - Q1 | MCP Dev Days (ADO 228660) | Sara / Aurea | Proposal - Event | 9/15 | Studio + virtual (Teams) | In planning | 3-hour livestream studio event with in-studio hosts and virtual presenters. Green room reserved. Should this be ingested?
FY27 - Q1 | .NET Conf 2026 (ADO 221377) | Cameron | Event | Week of 11/9 | Studio - all stages | In planning | Green room reserved.
FY27 - Q1 | PROPOSALS and any other upcoming projects | [5 empty] | ADO query: https://dev.azure.com/devrel/Studios/_queries/query/4ad8ccbc-1cfb-4b6b-b863-a492b382e206/

## Post-Prod & Pub
Post Production + Publication
Active projects | On Demand | Publish Date | Info/Discussion | Priority/Lift/Notes | Action items/Questions